## 2020-21
Project Name: DRAFT Ver.5 Horseshoe Lake, Barron County 2020-21 AEPP Grant Budget
Project Years: 2020-2021 Start Date: February 1, 2020 End Date: December 31, 2021.
Goal | Objective | Action | Task | Time Frame | Budget Line Numbers | LEAPS |  | Support Consultants |  | Lake Association (time) |  | Donated Services |  | Equipment/Paid Services |  | Sub-Total
[6 empty] | Time | Dollars | Who | Dollars | Time | Dollars | Who | Dollars | Who/What | Dollars
Aquatic Plant Community, Lake, and Shoreland Health | The current health and makeup of the aquatic plant community will be measured and compared to previous data | A whole-lake, warm water, point-intercept, aquatic plant survey will be completed in 2020 (the last one was done in 2013) | A summer, whole lake, point-intercept survey will be completed by Endangered Resource Sciences in 2020. | 2020 |  | 4 | 320 | ERS | 3375 | 4 | 48 |  |  |  |  | 3743
| Current water quality conditions will be documented and compared to prior data | Surface water quality testing including Total Phosphorus (TP), chlorophyll A (Chlr), water clarity (Secchi), Dissolved Oxygen (DO) and Temperature (Temp) Profilng will be completed monthly from May-October in both years of this project | Monthly collection of water quality samples May-October at the Deep Hole in both years. CLMN covers May-August, AEPP covers Sep&Oct. | 2020-2021 |  | 12 | 600 | SLOH | 232 | 84 | 1008 | Boat Use (28 hours) | 280 | Shipping | 120 | 2240
|  | Bottom phosphorus and iron testing will be completed three times between August and October in the first year of this project at three sites | Collection of water samples from near the bottom of the lake to determine phosphorus and iron content | 2020 |  | 8 | 400 | SLOH | 558 | 18 | 216 | Boat Use (9 hours) | 90 | Shipping | 100 | 1364
|  |  | Donated Van Dorn Use | 2020 | [7 empty] | Van Dorn Rental | 60 |  |  | 60
| Track lake level changes | Install a stff gauge and monitor lake level on at least a weekly basis | A staff gauge will be installed with assistance from the Polk County Land and Water Resource Department for the purpose of tracking water level changes. Volunteers will track water level on a weekly basis. | 2020-2021 |  | 2 | 160 |  |  | 36 | 432 | Polk Co. LWCD | 250 | Staff Gage | 100 | 942
| Changes in the shoreland as a result of July 2019 storms will be evaluated and compared to pre-storm data | A workshop/informational meeting will be held to discuss with property owners how damage to their property from July 2019 storms can be repaired in 2020 | The Lake Group will sponsor an informational meeting for property owners dealing with storm damage and how the Lake Group through various grant programs can help them | 2020 |  | 6 | 480 |  |  | 8 | 96 |  |  |  |  | 576
|  | A Coarse Woody Habitat Survey last completed in 2016 will be redone in 2020 | Re-evaluate the amount of coarse woody habitat in the lake, compare changes since the last survey in 2016, and determine what needs to be done to maintain it | 2020 |  | 8 | 400 |  |  | 4 | 48 | Boat Use (4 hours) | 40 |  |  | 488
AIS Education | The Lake Group constituency will be more aware and knowledgeable about AIS and how they can impact a lake. | AIS information including the dates and times of AIS workshops and related events, videos, and brochures will be posted on the lake group's webpage and Facebook page | Identify and post AIS education and information to increase awareness and knowledge of the constituency on the Lake Groups webpage and/or Facebook page | 2020-2021 |  | 6 | 300 |  |  | 24 | 288 |  |  |  |  | 588
| Property owners will monitoring and remove AIS from around their docks and on their shoreland. | Property owners will be taught how to identify and remove AIS from around their docks and on their shoreland by offering an AIS idenitifcation and Removal Training Session in each year of this project | Volunteers on the lake will sponsor at least one workshop annually to teach lake property owners how to identify and then remove AIS from the waters near their docks | 2020-2021 |  | 16 | 800 |  |  | 16 | 192 | Boat Use (8 hours) | 80 |  |  | 1072
AIS Prevention | AIS signage and display of other information at the public access will be reviewed an evaluated for effectiveness | A review existing AIS Signage at the public access will be completed in 2020 | A review of the AIS signage and other aspects of the public access will be completed using the WDNR Aquatic Invasive Species Signage Report - Form 3200-152 | 2020 | [5 empty] | 8 | 96 |  |  |  |  | 96
| AIS signage at the public access will be repaired, replaced, or updated to improve effectiveness. In addition, a 4X4 ZM Decontamination Sign will be installed | Existing AIS signage and information at the public access will be repaired, replaced, modified, or added anew | Based on findings from the review of AIS signage, what is posted/available at the public access will be updated, including the installation of a 4X4 Decontamination Sign and associated equipment. | 2020-2021 | [5 empty] | 16 | 192 |  |  | Materials | 350 | 542
| More focused efforts to monitor for and protect the lake from zebra mussels will be completed | The Lake Group will install at least one ZM plate sampler in the lake, train property owners to look for ZM when removing their docks in the fall | Install a ZM plate sampler, set up a decontamination station, and provide education to property owners about how to look for ZM | 2020-21 |  | 4 | 320 |  |  | 32 | 384 | Boat Use (12 hours) | 120 |  |  | 824
| Lake users launching or removing boats and other watercraft from the lake will be educated on how to prevent the spread of AIS from one lake to the next | A watercraft inspection program following Clean Boats Clean Waters (CBCW) guidelines will be implemented in each year of this project | The Lake Group will complete 200 hours of combined paid and volunteer CBCW time at the public access in each year of this project. All data will be submitted to the SWIMS database | 2020-2021 | CBCW Inspections will be covered with individual CBCW grants applied for by the Lake Group | [10 empty] | 0
| New AIS that may get introduced to the lake will not go undetected | Trained AIS monitors will complete visual surveys of the lake littoral zone, adjacent shoreline, and surrounding area at least three times between June and September each year | Trained volunteers will seach the littoral zone of the lake and adjacent shoreland for AIS following CLMN AIS Monitoring guidelines. All data will be submitted to the SWIMS database. | 2020-2021 |  | 6 | 480 |  |  | 48 | 576 | Boat Use (24 hours) | 240 |  |  | 1296
| Purple loosestrife will not be allowed to spread and/or increase its density on the shores of the lake | At least one survey of the shoreland looking for purple loosestrife will completed in each year of this project. | Visual mapping of purple loosestrife, including GPS points will be completed by the Lake Group in both years of this project. Purple loosestrife will be physically removed if practical | 2020-2021 |  | 6 | 300 |  |  | 16 | 192 | Boat Use (8 hours) | 80 |  |  | 572
AIS Management Planning Support | Hybrid watermilfoil (HWM) management planning will be completed by a Consultant in cooperation with the Lake Group, other stakeholders, and WDNR | Management planning for the control of HWM will be completed in both years of this project | Final treatment planning in 2020, preliminary and final treatment planning in 2021 will be completed as a part of this project. 2022 management planning will be included in the update of the APM Plan | 2020-2021 |  | 16 | 1280 |  |  | 12 | 144 |  |  |  |  | 1424
| WDNR herbicide application permits and/or harvesting permits will be prepared by the Consultant in cooperation with the Lake Group, other stakeholders, and WDNR | The apropriate aquatic plant management permits will be completed and submitted to the WDNR for approval | The Consultant will complete and WDNR herbicide application permit for HWM | 2020-2021 |  | 8 | 400 |  |  | 8 | 96 |  |  | Permit Application Fee (2 acres in 2020, 5 acres in 2021) | 215 | 711
| Any areas of HWM that are chemically treated will have both pre and post-treatment, point-intercept, aquatic plant survey work completed. | Pre and post-treatment, point-intercept, aquatic plant survey work will completed by a plant specialist in each year of this project | Pre and post HWM chemical treatment surveys will be completed in 2020 and 2021 by ERS | 2020-2021 |  | 4 | 320 | ERS | 2250 | 16 | 192 |  |  |  |  | 2762
| The distribution and density of HWM in the lake will be quanitified in the fall | Fall HWM bedmapping will be completed by a plant specialist in each year of this project | Fall HWM bed mapping surveys will be completed in 2020 and 2021 by ERS | 2020-2021 |  | 4 | 320 | ERS | 3000 | 16 | 192 | Donation from voluntary lauch fees over two years | 400 |  |  | 3912
| The existing Aquatic Plant Management Plan for the lake will be updated by the Consultant in cooperation with the Lake Group, other stakeholders, and WDNR. | A consultant will complete an update of the existing APM Plan based on new point-intercept data from the lake. | The Consultant will update the APM Plan in 2021 | 2021 |  | 64 | 5120 |  |  | 16 | 192 |  |  |  |  | 5312
Project Management | Project materials and results will be shared with the lake constituency and the general public | Lake Group personnel will maintain current and accurate posting of grant related documents on the webpage and/or Facebook | Accurate and up-to-date grant related information and HWM management planning and implementation will be posted on the Lake Group webpage/Facebook page | 2020-2021 |  | 4 | 200 |  |  | 24 | 288 |  |  |  |  | 488
| General project management including sponsor and consultant administrative support, mileage, and materials will be documented. | General project management provided by the Consultant includes meeting attendance, daily phone and email, annual project updates, mileage, materials, and printing costs. | The consultant will attend at least three meetings of the Lake Group during this project, provide general management support, and prepare of end of year summary reports for 2020 and 2021 | 2020-2021 |  | 24 | 1920 | [6 empty] | Mileage/Misc Expenses | 300 | 2220
|  | General project and administrative support provided by the Lake Group includes daily interaction with the project consultant, data and information tracking and documentation, filing for reimbursements, | Volunteers will administer this project including record keeping and final reimbursement requests | 2020-2021 | [5 empty] | 120 | 1440 |  |  | Printing and Postage | 300 | 1740
[6 empty] | 202 | 14120 |  | 9415 | 526 | 6312 |  | 1640 |  | 1485 | 32972
|  | Total Project Cost | 32972 | [11 empty] | 32972
|  | State Share Requested (75%) | 24729 |  |  |  | AIS - Aquatic Invasive Species
|  | Sponsor Share (25%) | 8243 |  |  |  | PL - purple loosestrife
CLP - curly-leaf pondweed
|  | Match Included in this Application | 7952 |  |  |  | HWM-Hybrid watermilfoil
|  | Match Still Needed (over two years) | 291 |  |  |  | PI survey - Point-intercept survey
ERS - Endangered Resource Services (Plant survey consultant, Matt Berg)
SLOH - WI State Lab of Hygiene (water sample processing)
CBCW - Clean Boats Clean Waters