## 2020-21
Project Name: DRAFT Echo Lake, Barron County 2020-21 AEPP Grant Budget 11-25-2019
Project Years: 2020-2021 Start Date: February 1, 2020 End Date: December 31, 2021.
Goal | Objective | Action | Task | Time Frame | Budget Line Numbers | LEAPS |  | Support Consultants |  | Lake Association (time) |  | Donated Services |  | Equipment/Paid Services |  | Sub-Total
[6 empty] | Time | Dollars | Who | Dollars | Time | Dollars | Who | Dollars | Who/What | Dollars
Aquatic Plant Community, Lake, and Shoreland Health | Current water quality conditions will be documented and compared to prior data | Surface water quality testing including Total Phosphorus (TP), chlorophyll A (Chlr), water clarity (Secchi), Dissolved Oxygen (DO) and Temperature (Temp) Profilng will be completed monthly from May-October in both years of this project | Monthly collection of water quality samples May-October | 2020-2021 | 1 | 8 | 400 | SLOH | 232 | 60 | 720 | Boat Use (24 hours) | 240 | Shipping | 75 | 1667
|  | A Coarse Woody Habitat Survey will be done in 2020 | Re-evaluate the amount of coarse woody habitat in the lake, compare changes since the last survey, and determine what needs to be done to maintain it | 2020 | 2 | 8 | 400 |  |  | 4 | 48 | Boat Use (4 hours) | 40 |  |  | 488
| Shoreland disturbed by the July 2019 storms will be reviewed and recommendations made for repair. | A meeting will discuss how property owners can repair storm damage and materials for erosion control on properties with disturbed/exposed soil will be provided in at least 2020 | Hold a special meeting of property owners to discuss storm damage repair projects. | 2020 | 3 | 6 | 480 |  |  | 8 | 96 |  |  |  |  | 576
AIS Education | The Lake Group constituency will be more aware and knowledgeable about AIS and how they can impact a lake. | AIS information including the dates and times of AIS workshops and related events, videos, and brochures will be posted on the lake group's webpage and Facebook page | Identify and post AIS education and information to increase awareness and knowledge of the constituency on the Lake Groups webpage and/or Facebook page | 2020-2021 | 4 | 4 | 200 |  |  | 8 | 96 |  |  |  |  | 296
| Property owners will monitor and remove AIS from around their docks and on their shoreland. | Property owners will be taught how to identify and remove AIS from around their docks and on their shoreland by offering an AIS idenitifcation and Removal Training Session in each year of this project | Volunteers on the lake will sponsor at least one workshop annually to teach lake property owners how to identify and then remove AIS from the waters near their docks | 2020-2021 | 5 | 4 | 200 |  |  | 12 | 144 | Boat Use (6 hours) | 60 |  |  | 404
AIS Prevention | AIS signage and display of other information at the public access will be reviewed an evaluated for effectiveness | A review existing AIS Signage at the public access will be completed in 2020 | A review of the AIS signage and other aspects of the public access will be completed using the WDNR Aquatic Invasive Species Signage Report - Form 3200-152 | 2020 | 6 |  |  |  |  | 4 | 48 |  |  |  |  | 48
| AIS signage at the public access will be repaired, replaced, or updated to improve effectiveness | Existing AIS signage and information at the public access will be repaired, replaced, modified, or added anew | Based on findings from the review of AIS signage, what is posted/available at the public access will be updated. | 2020-2021 | 7 |  |  |  |  | 8 | 96 |  |  | Materials | 200 | 296
| Lake users launching or removing boats and other watercraft from the lake will be educated on how to prevent the spread of AIS from one lake to the next | A watercraft inspection program following Clean Boats Clean Waters (CBCW) guidelines will be implemented in each year of this project | The Lake Group will complete 100 hours of combined paid and volunteer CBCW time at the public access in each year of this project. All data will be submitted to the SWIMS database | 2020-2021 | 8 |  |  |  |  | 100 | 1200 |  |  | 100 hours of paid CBCW time | 1200 | 2400
| New AIS that may get introduced to the lake will not go undetected | Trained AIS monitors will complete visual surveys of the lake littoral zone, adjacent shoreline, and surrounding area at least three times between June and September each year | Trained volunteers will seach the littoral zone of the lake and adjacent shoreland for AIS following CLMN AIS Monitoring guidelines. All data will be submitted to the SWIMS database. | 2020-2021 | 9 | 12 | 960 |  |  | 36 | 432 | Boat Use (18 hours) | 180 |  |  | 1572
| People removing docks and boatlifts in the fall will be educated on how to check their equipment and what to look for. | The ELA will reach out to the companies that remove docks and boat lifts in the fall and too its constituency to encourage them to inspect for ZM in the fall of each year. | ELA representatives will contact local dock and boatlift removal companies and share information about inspecting for ZMs. The ELA will also provide training for its constituency. | 2020-2021 | 10 | 4 | 200 |  |  | 16 | 192 |  |  |  |  | 392
AIS Management Planning Support | Eurasian watermilfoil (EWM) management planning will be completed by a Consultant in cooperation with the Lake Group, other stakeholders, and WDNR | Management planning for the control of EWM will be completed in both years of this project | Final treatment planning in 2020, preliminary and final treatment planning in 2021 will be completed as a part of this project. | 2020-2021 | 11 | 20 | 1600 |  |  | 12 | 144 |  |  |  |  | 1744
| WDNR herbicide application permits and/or harvesting permits will be prepared by the Consultant in cooperation with the Lake Group, other stakeholders, and WDNR | The apropriate aquatic plant management permits will be completed and submitted to the WDNR for approval | The Consultant will complete and WDNR herbicide application permit for EWM | 2020-2021 | 12 | 8 | 400 |  |  | 8 | 96 |  |  | Permit Application Fee (2 acres for 2 yrs) | 140 | 636
| Any areas of EWM that are chemically treated will have both pre and post-treatment, point-intercept, aquatic plant survey work completed. | Pre and post-treatment, point-intercept, aquatic plant survey work will completed by a plant specialist in each year of this project that chemical treatment is used | Pre and post EWM chemical treatment surveys will be completed in 2021 by ERS | 2021 | 13 | 6 | 480 | ERS | 1000 | 4 | 48 |  |  |  |  | 1528
| The distribution and density of EWM in the lake will be quanitified in the lake | Summer and Fall EWM bedmapping meandering surveys will be completed by a plant specialist in each year of this project | Summer and Fall EWM bedmapping meandering surveys will be completed in 2020 and 2021 by ERS | 2020-2021 | 14 | 8 | 640 | ERS | 2500 | 8 | 96 |  |  |  |  | 3236
Project Management | Project materials and results will be shared with the lake constituency and the general public | Lake Group personnel will maintain current and accurate posting of grant related documents on the webpage and/or Facebook | Accurate and up-to-date grant related information and EWM management planning and implementation will be posted on the Lake Group webpage/Facebook page | 2020-2021 | 15 |  |  |  |  | 12 | 144 |  |  |  |  | 144
| General project management including sponsor and consultant administrative support, mileage, and materials will be documented. | General project management provided by the Consultant includes meeting attendance, daily phone and email, annual project updates, mileage, materials, and printing costs. | The consultant will attend at least three meetings of the Lake Group during this project, provide general management support, and prepare of end of year summary reports for 2020 and 2021 | 2020-2021 | 16 | 28 | 2240 | [6 empty] | Mileage/Misc Expenses | 300 | 2540
|  | General project and administrative support provided by the Lake Group includes daily interaction with the project consultant, data and information tracking and documentation, filing for reimbursements, | Volunteers will administer this project including record keeping and final reimbursement requests | 2020-2021 | 17 |  |  |  |  | 45 | 540 |  |  | Printing and Postage | 150 | 690
[6 empty] | 116 | 8200 |  | 3732 | 345 | 4140 |  | 520 |  | 2065 | 18657
|  | Total Project Cost | 18657 | [11 empty] | 18657
|  | State Share Requested (75%) | 13992.75 |  |  |  | AIS - Aquatic Invasive Species
|  | Sponsor Share (25%) | 4664.25 |  |  |  | PL - purple loosestrife
CLP - curly-leaf pondweed
|  | Match Included in this Application | 4660 |  |  |  | EWM-Hybrid watermilfoil
|  | Match Still Needed (over two years) | 4.25 |  |  |  | PI survey - Point-intercept survey
ERS - Endangered Resource Services (Plant survey consultant, Matt Berg)
SLOH - WI State Lab of Hygiene (water sample processing)
CBCW - Clean Boats Clean Waters