## 2020
Echo Lake AEPP Grant- 2020
Task | Description | Lake Organization Responsibilities | Time | Boat Use | When | Consultant Responsibilities | Time | When | External Costs | When
1 | Surface water sampling including TP, Chl-A, Secchi, DO, and Temp May- Oct | Monthly collection of water quality samples May-October, and entering data into SWIMS database | 30 | 12 | May- Oct | Volunteer training and extended chemistry supply preparation and delivery | 4 | May, Sept, & Oct | SLOH processing of water chemistry samples- $116, shipping- $37.50 | May- Oct
2 | Re-evaluation of coarse woody habitat in and around the lake | Volunteer assistance for woody habitat survey | 4 | 4 | Spring or Fall | Conduct coarse woody habitat survey and process data collected | 8 | Spring or Fall | NA | NA
3 | Meeting to discuss 2019 storm damage repair projects | Hold special meeting for property owners | 8 |  | May-June | Attend meeting and educate property owners on repair projects | 6 | May-June | NA | NA
4 | Create and post AIS education and information on ELA webpage/ Facebook | Create and post AIS education and information on ELA webpage/ Facebook | 4 |  | Apr-Oct | Consultant support and assistance creating/finding educational material | 2 | Apr- Oct | NA | NA
5 | At least one summer workshop to teach property owners how to identify AIS and physically remove them | Sponsor AIS workshop | 6 | 3 | Jun-Aug | Consultant support and assistance for workshop | 2 | Jun- Aug | NA | NA
6 | Review AIS signage and other aspects of public access at the public boat landing | Complete AIS signage and public access review using WDNR Aquatic Invasive Species Signage Report - Form 3200-152 | 4 |  | Apr-Sept | NA | NA | NA | NA | NA
7 | Repair, and replace AIS signage at the public boat landing | Repair, and replace AIS signage at the public boat landing based on findings of review | 4 |  | 2020 | NA | NA | NA | Materials- $100 | 2020
8 | 100 hours of CBCW boat inspection and data entry | Volunteer time and coordinate paid CBCW inspectors and data entry | 50 |  | May- Oct | NA | NA | NA | Paid CBCW inspectors (50 hrs)- $600 | May- Oct
9 | CLMN shoreline and littoral zone AIS monitoring | Trained volunteer surveys of shoreline and littoral zone and entry of all data into SWIMS | 18 | 9 | May-Oct | Volunteer training and support for AIS surveys | 6 | May-Oct | NA | NA
10 | Zebra mussel education and dock out training | Contact local dock and boatliift removal companies and share information about zebra mussel inspection. Provide training and educational material to constituents | 8 |  | Aug-Oct | Consultant support and assistance for training and educational materials | 2 | Aug- Oct | NA | NA
11 | Final 2020 EWM management planning for chemical treatment | review and approval of EWM management plan | 6 |  | Feb-Apr | Prepare final chemical management plan for EWM | 10 | Feb-Apr | NA | NA
12 | Preparation of WDNR herbicide application permit | Review of and assistance preparing WDNR permit | 4 |  | Mar-May | Prepare the WDNR permit | 4 | Mar-May | Permit fee- $70 | Mar-May
13 | Pre Post Chemical Treatment Plant Survey | NA
14 | Summer and Fall EWM bed mapping locating EWM beds, high density areas, and individual EWM plants | Review survey reports | 4 |  | Sept-Dec | General support from Consultant for surveys | 4 | Aug- Nov | Complete fall EWM bed mapping Survey and prepare the summary report (ERS)- $1,250 | 2020
15 | Informing ELA members of grant and management activities | Posting and maintaining information on ELA webpage/ Facebook page | 6 |  | 2020 | NA | NA | NA | NA | NA
16 | ELA Meetings | NA |  |  | NA | Preparation, travel time, and participation in at least one ELA meeting to discuss management planning and preparation of end of year management summary report by consultant | 14 | 2020 | Mileage and misc. expenses- $150 | 2020
17 | General project management and administration | ELA volunteer administration of this project including general record keeping and final reimbursement requests | 20 |  | 2020 | NA | NA | NA | Printing and postage- $75 | 2020
|  |  | 176 | 28 |  |  | 62
SLOH- State Lab of Hygiene
|  | NAS- Northern Aquatic Services (Herbicide Applicator) |  |  |  | APM - Aquatic Plant Management
|  | ERS - Endangered Resource Services (aquatic plant surveyor) |  |  |  | AIS - Aquatic Invasive Species
|  | DO/temp - Dissolved oxygen/temperature profiles |  |  |  | CLMN - Citizen Lake Monitoring Network
|  | EWM - Eurasian watermilfoil |  |  |  | PI- Point-Intercept
ELA- Echo Lake Association

## 2021
Echo Lake AEPP Grant- 2021
Task | Description | Lake Organization Responsibilities | Time | Boat Use | When | Consultant Responsibilities | Time | When | Sub-Contractor Responsibilities | When
1 | Surface water sampling including TP, Chl-A, Secchi, DO, and Temp May- Oct | Monthly collection of water quality samples May-October, and entering data into SWIMS database | 30 | 12 | May- Oct | Volunteer training and extended chemistry supply preparation and delivery | 4 | May, Sept, & Oct | SLOH processing of water chemistry samples- $116, shipping- $37.50 | May- Oct
2 | Re-evaluation of coarse woody habitat in and around the lake | NA
3 | Meeting to discuss 2019 storm damage repair projects | NA
4 | Create and post AIS education and information on ELA webpage/ Facebook | Create and post AIS education and information on ELA webpage/ Facebook | 4 |  | Apr-Oct | Consultant support and assistance creating/finding educational material | 2 | Apr- Oct | NA | NA
5 | At least one summer workshop to teach property owners how to identify AIS and physically remove them | Sponsor AIS workshop | 6 | 3 | Jun-Aug | Consultant support and assistance for workshop | 2 | Jun- Aug | NA | NA
6 | Review AIS signage and other aspects of public access at the public boat landing | Complete AIS signage and public access review using WDNR Aquatic Invasive Species Signage Report - Form 3200-152 | NA
7 | Repair, and replace AIS signage at the public boat landing | Repair, and replace AIS signage at the public boat landing based on findings of 2020 review | 4 |  | 2021 | NA | NA | NA | Materials- $100 | 2021
8 | 100 hours of CBCW boat inspection and data entry | Volunteer time and coordinate paid CBCW inspectors and data entry | 50 |  | May- Oct | NA | NA | NA | Paid CBCW inspectors (50 hrs)- $600 | May- Oct
9 | CLMN shoreline and littoral zone AIS monitoring | Trained volunteer surveys of shoreline and littoral zone and entry of all data into SWIMS | 18 | 9 | May-Oct | Volunteer training and support for AIS surveys | 6 | May-Oct | NA | NA
10 | Zebra mussel education and dock out training | Contact local dock and boatliift removal companies and share information about zebra mussel inspection. Provide training and educational material to constituents | 8 |  | Aug-Oct | Consultant support and assistance for training and educational materials | 2 | Aug- Oct | NA | NA
11 | Preliminary and final 2021 EWM management planning for chemical treatment | review and approval of EWM management plan | 6 |  | Feb-Apr | Prepare final chemical management plan for EWM | 10 | Feb-Apr | NA | NA
12 | Preparation of WDNR herbicide application permit | Review of and assistance preparing WDNR permit | 4 |  | Mar-May | Prepare the WDNR permit | 4 | Mar-May | Permit fee- $70 | Mar-May
13 | Pre/Post-treatment point-intercept surveys | Volunteer to assist Aquatic Plant Surveyor during the readiness survey | 4 |  | 2021 | Consultant support for pre/post-tretment PI survey work | 6 | Apr-June | complete pre/post treatment survey work (ERS)- $1,000 | May-June
14 | Summer and Fall EWM bed mapping locating EWM beds, high density areas, and individual EWM plants | Review survey reports | 4 |  | Sept-Dec | General support from Consultant for surveys | 4 | Aug- Nov | Complete fall EWM bed mapping Survey and prepare the summary report (ERS)- $1,250 | 2021
115 | Informing ELA members of grant and management activities | Posting and maintaining information on ELA webpage/ Facebook page | 6 |  | 2021 | NA | NA | NA | NA | NA
16 | ELA Meetings | NA |  |  | NA | Preparation, travel time, and participation in at least 2 ELA meetings to discuss management planning and preparation of end of year management summary report by consultant | 14 | 2021 | Mileage and misc. expenses- $150 | 2021
17 | General project management and administration | ELA volunteer administration of this project including general record keeping and final reimbursement requests | 25 |  | 2021 | NA | NA | NA | Printing and postage- $75 | 2021
|  |  | 169 | 24 |  |  | 54
SLOH- State Lab of Hygiene
|  | NAS- Northern Aquatic Services (Herbicide Applicator) |  |  |  | APM - Aquatic Plant Management
|  | ERS - Endangered Resource Services (aquatic plant surveyor) |  |  |  | AIS - Aquatic Invasive Species
|  | DO/temp - Dissolved oxygen/temperature profiles |  |  |  | CLMN - Citizen Lake Monitoring Network
|  | EWM - Eurasian watermilfoil |  |  |  | PI- Point-Intercept
ELA- Echo Lake Association